## Gantt Chart
Miromio Café Online Menu & Ordering System — Gantt Chart
Role | Task | Sep 1–7 | Sep 8–14 | Sep 15–21 | Sep 22–28 | Sep 29–Oct 5 | Oct 6–8
Customer | 1.1 View Menu | Sep 1–5
Customer | 1.2 View Café Information | Sep 3–7
Customer | 1.3 Place Order |  | Sep 8–14
Customer | 1.4 View Order Status |  |  |  | Sep 22–Oct 5
Customer | 1.5 Receive Ready Notification |  |  |  |  | Oct 1–8
Online Ordering System | 2.1 Display Menu & Café Information | Sep 1–7
Online Ordering System | 2.2 Receive & Record Order |  | Sep 8–14
Online Ordering System | 2.3 Check Order |  |  | Sep 15–18
Online Ordering System | 2.4 Send Order to Café Staff |  |  | Sep 18–21
Online Ordering System | 2.5 Send Ready Notification |  |  |  |  | Oct 1–8
Café Staff | 3.1 Manage Prices/Menu | Sep 1–7
Café Staff | 3.2 Receive & Review Order |  |  | Sep 18–21
Café Staff | 3.3 Prepare Order |  |  |  | Sep 22–30
Café Staff | 3.4 Update Order Status |  |  |  |  | Sep 29–Oct 5
Legend | Customer tasks | System tasks | Café staff tasks